## Slide 1
DIB / CET MONTHLY PERFORMANCE
Delivery progressed, with resilience gaps requiring attention
Executive outcome across IB / MB, FinnOne and HFLMS
September 2026 • Source: supplied platform and squad reports
1
✓
98
delivered / completed
◉
285
reported demands
▦
68
backlog items
↗
67
in progress
◉ IB / MB
25 / 113 (22.1%)
delivered / completed
16.99B volume
99.9% availability • DR Tested
◆ FinnOne
50 / 122 (41.0%)
delivered / completed
3.24B volume
100% availability • DR Unavailable
⌂ HFLMS
23 / 50 (46.0%)
delivered / completed
1.24B volume
100% availability • DR Unavailable
Management focus
MB incident controls and backlog capacity need attention. FinnOne and HFLMS require interim recovery controls before the 2027 DR upgrades.
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. ¹Completed / total demand is a portfolio snapshot share, not a monthly delivery rate. Totals are arithmetic sums of reported platform portfolios, without demand-ID deduplication. 98/285=34.4%. Other states: 24 new demand, 4 baseline 0, 24 dropped. Volumes remain separate because currency and cross-platform overlap are unspecified. Source health labels are Green for all platforms. Management priorities are analytical recommendations.

## Slide 2
DIB / CET MONTHLY PERFORMANCE
IB / MB supports 16.99B in business volume
Delivery continues while Mobile Banking reliability needs closer oversight
September 2026 • Source: supplied platform and squad reports
2
Chart: 
| Retail | SME
Reported volume | 7.83 | 9.16
54% of reported volume comes from SME
Delivered
25
In progress
23
Backlog
27
New demand
24
Dropped
14
113 demands
99.9% availability
DR tested
MB: 6 major + 1 minor incidents
IB: 2 minor incidents
Operational outcome
15 planned deployments. Service continuity maintained during ~48 hours of intermittent MB degradation attributed to DDoS threshold exceedance.
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. Planned outages/deployments: IB 5, MB 10. Planned downtime: IB 2h50m, MB 3h15m. Unplanned outages: MB 1. The source reports ~48 hours of intermittent degradation and successful mitigation, not 48 hours of total downtime. Infrastructure: MB CPU 7.97%, memory 35.64%, storage 66.10%. IB CPU 5.01%, memory 52.87%, storage 50.17%. DR available yes, tested, environment readiness validated and recovery procedures confirmed. Source reports healthy infrastructure and monitored reliability. SME share 9.16/16.99=53.9%.

## Slide 3
DIB / CET MONTHLY PERFORMANCE
FinnOne combines 50 completed demands with zero outages
3.24B reported September volume, with PF contributing approximately 72%
September 2026 • Source: supplied platform and squad reports
3
Chart: 
| AF | AF-EV | CC | PF | SBF
Reported volume | 0.63 | 0.02 | 0.19 | 2.33 | 0.07
Completed
50
In progress
29
Backlog
29
Baseline 0
4
Dropped
10
24,981
transaction count
100% availability
No critical or major incidents
DR unavailable
Upgrade planned for 2027
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. Total demands 122. Exact September volume 3,242,716,155.49. Rounded component volumes sum to 3.24B. PF share 2.33/3.24=71.9%. Planned outages 0, unplanned outages 0, planned downtime 0 hours, unplanned downtime 0. Reliability unchanged and stable operational posture. CPU <10%, memory <60%, capacity healthy within operating thresholds. No DR available, upgrade planned 2027. Source target is sustain monthly processing above 3.0 billion, not a forecast. Product abbreviations preserved from source.

## Slide 4
DIB / CET MONTHLY PERFORMANCE
HFLMS maintained continuity through secondary-server failover
23 completed demands. September volume eased 10.8% from August
September 2026 • Source: supplied platform and squad reports
4
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Reported volume | 1.08 | 1.2 | 0.84 | 1.1 | 0.97 | 1.01 | 1.57 | 1.39 | 1.24
1.24B
774 transactions
50 demands
23 completed / 15 in progress
12 backlog / 0 baseline 0
1 major incident
12 minutes unplanned downtime
DR unavailable
Upgrade planned for 2027
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. Exact September volume 1,244,030,273. Source monthly values are rounded to two decimal billions. August-to-September change (1.24/1.39-1)=-10.8%, calculated from rounded figures. July peak 1.57B, March low 0.84B. 0 planned outages, 1 unplanned outage, 0 planned downtime, 12 minutes unplanned downtime. Application server dxb01-vwp-lmsa2 stopped responding and returned Server Too Busy. Secondary server took load and prevented total environment outage. No critical incidents, one major incident, reliability monitored. CPU <40%, memory <25%, storage <70%. Source availability 100% needs reconciliation with 12 minutes downtime.

## Slide 5
DIB / CET MONTHLY PERFORMANCE
The delivery pipeline spans releases, controls and integrations
Selected initiatives reported in September. Pipeline stages guide the next management review
September 2026 • Source: supplied platform and squad reports
5
◉ IB / MB
LIVE / DELIVERED
Skywards cards removal from MB
3x3 Drop 4 – Releases 1 & 2
TAB-52 – Tablet AOF audit requirement
IN PROGRESS
EFR cost enhancements – SIT
SWIFT GPI – Regression
Input Validations – Development
EFMS Upgrade – UAT
Emirati Card – SIT / UAT
◆ FinnOne
LIVE / DELIVERED
LL / LG flag field amendment
Multiple Rate Changes service request
Supplementary Card mobile number / email capture
IN PROGRESS
RTA Integration – Design
PDC Remittance – UAT
EFR for PDC – Design
⌂ HFLMS
LIVE / DELIVERED
No named live initiatives supplied
IN PROGRESS
HF48 Forward Ijara Freehold Phase 2
Dedup logic controls in customer onboarding*
Duplicate CIF: linkage of closed customer*
* HFLMS + Core Banking. Source gives no stage for these initiatives. Names and abbreviations retain the source terminology.
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. These are selected named initiatives, not a complete list of the 98 delivered/completed items or 67 in progress. The source spells Emirati Card. LL/LG and CIF expansion not assumed. IB/MB source: Removal of Skywards Cards from Mobile Banking; 3x3 Drop 4 – Release 1 & Release 2; TAB-52 – Tablet AOF Audit Requirement. FinnOne source: Field Amendment for LL and LG flags; Multiple Rate Changes service request; Supplementary Card Mobile No. Email ID Capture.

## Slide 6
DIB / CET MONTHLY PERFORMANCE
Management priorities: capacity and recovery readiness
Recommended management actions based on September reporting
September 2026 • Source: supplied platform and squad reports
6
!
MB reliability
Review the DDoS threshold event and mitigation controls
▦
Backlog capacity
Prioritize 68 backlog items across the three portfolios
⟳
Recovery exposure
Agree interim recovery controls for FinnOne and HFLMS
✓
Delivery progression
Review readiness of SIT, UAT and regression items
Infrastructure has reported headroom
MB / IB
CPU 7.97% / 5.01% Memory 35.64% / 52.87%
Storage 66.10% / 50.17%
FinnOne
CPU <10% Memory <60%
Storage Not supplied
HFLMS
CPU <40% Memory <25%
Storage <70%
Notes: Source: user-provided September 2026 IB/MB, FinnOne and HFLMS portfolio overview images. Next-review evidence: incident closure, customer impact and effectiveness of MB controls; approved pickup plan for IB/MB 27, FinnOne 29 and HFLMS 12; recovery ownership, test evidence and 2027 milestones; release dates, blockers and acceptance decisions. Demand dots each represent one reported item. Data interpretation: source labels all platforms Green. HFLMS reports 100% availability alongside 12 minutes unplanned downtime. IB/MB reports 99.9% alongside ~48 hours intermittent MB degradation. These metrics may use different denominators or service scopes. Reconcile definitions without substituting an invented availability rate. No prior-month demand snapshot, demand aging, capacity allocation, costs, benefits or dates supplied. Delivery share is a portfolio composition measure and cannot establish throughput growth, ROI or delivery efficiency. Volumes are business transaction volumes, not revenue. Summing portfolios assumes no cross-platform duplicate demand IDs and needs validation before an enterprise unique-demand total. Recommendations do not imply approved owners or commitments.

## Slide 7
DIB / CET MONTHLY PERFORMANCE
AF squad: four initiatives in SIT / UAT
September status snapshot. Two initiatives have business sign-off.
September 2026 • Source: supplied platform and squad reports
7
◉ 4 solution finalization
DMGT-1325: Early settlement KFS trigger
DMGT-2063: Hybrid / country-of-origin flags
DMGT-679: Digital AECB and KFS
Fourth initiative not named in source
⚙ 4 development
DMGT-267: Facial recognition for ETB
DMGT-1052: New Takaful products
DMGT-950: RTA Integration
DMGT-2583: AF switch to standard rates
✓ 2 SIT
DMGT-55 / DMGT-97
Down payment and fee collection
Additional ILOE premium collection
◆ 2 UAT
DMGT-91: Rate / campaign master
Adding guarantor in FinnOne
Guarantor demand ID not supplied
✓ 2 business sign-off
DMGT-2480: Wataniya T&C in AF ILOE consent
DMGT-2384: Early Settlement SMS
▦ 4 backlog
Awaiting pickup
30 Sep planned: DMGT-2583
4 Oct planned: DMGT-2480 / DMGT-2384
Actual go-live confirmation required
Squad counts are reported stage counts and may overlap the platform portfolio.
Notes: Source: AF executive summary attachment IMG_212267D2-D987-4FA7-B317-11571926A8EA.jpeg. Four solution-finalization items reported but only three named. Adding Guarantor has DMGT without number in source. Source reports 18 stage-counted initiatives (4+4+2+2+2+4), not independently deduplicated. DMGT-2583 is listed under development and planned 30 September 2026. DMGT-2480 and DMGT-2384 planned 4 October 2026. Dates are plans, not confirmed releases.

## Slide 8
DIB / CET MONTHLY PERFORMANCE
AF delivery timeline: September 2025–August 2026
Twelve months of milestones. Read across each row, then continue below.
September 2026 • Source: supplied platform and squad reports
8
✓ Sep 2025
Disclosure notification for STL
›
✓ Oct 2025
Q4 rate deployment
Subvention campaign in FinnOne
›
✓ Nov 2025
Updated SLA logic
POD
Job-loss Takaful mapping
›
✓ Dec 2025
Rhoon Integration
EV Tesla PF update
Ramadan-to-standard profit rate switch
IRR value modification
✓ Jan 2026
Map dealer under FD group
›
✓ Feb 2026
EMI deferment fee
AF campaign enhancement
New Ramadan rates 2026
Abu Dhabi Motors profit-rate update
›
✓ Mar 2026
Sharia terminology update in FinnOne
AF Profit Ramadan Rate
›
✓ Apr 2026
WhatsApp Dealer
Frontline employer special-rate change
Standard rate revision
✓ May 2026
Finance amount transfer: I2I
Tenure control for subvention applications
Employer rates / EAR changes
WhatsApp Disable
Golden VISA
›
✓ Jun 2026
Motorcycle field validation
›
✓ Jul 2026
ILOE premium update
Frontline campaign extension
Chassis number / flat-rate validation at PDOC
AF Summer Campaign 2026
DMGT-2372: Frontline Hero expiry
›
✓ Aug 2026
PGL: ILOE
PGL: POD rate issue
Tesla rate revision
Notes: Sources: supplied AF roadmap screenshots, September 2025–February 2026 and March–August 2026. These are historical milestones, not September 2026 delivery counts. Names retained from the previously reviewed AF roadmap.

## Slide 9
DIB / CET MONTHLY PERFORMANCE
PF squad: six initiatives remain in solution design
September status snapshot. One initiative has business sign-off.
September 2026 • Source: supplied platform and squad reports
9
◉ 6 solution design
83: RAO salary check in liability settlement
49: Early settlement methodology
1336: Early settlement KFS
2557: LC retention scheme
1708: Flexi Salary after-sales (LEAN)
1021: EFR for NTB / ETB
⚙ 1 development
DMGT-91
Business pricing updates in FinnOne
◆ 1 UAT
DMGT-106
LC PDC settlement remittance to the correct account
✓ 1 business sign-off
DMGT-56
FTS enablement in all STL segments
Planned go-live: 4 October 2026
Actual release confirmation required
▦ 3 backlog
Pickup depends on delivery of the current set of demands
↻ 8 open points
Tracked separately for follow-up
Treat as tracking items until demand scope and unique IDs are confirmed
Solution-design numbers use the DMGT prefix. Squad counts are separate from platform totals.
Notes: Source: PF executive summary IMG_607B2DBC-EFD7-4E54-BD48-3BCC7F4B5C7E.jpeg. Six solution-design demand IDs DMGT-83,49,1336,2557,1708,1021; one development DMGT-91, one UAT DMGT-106, one business sign-off DMGT-56, three backlog and eight open-point tracking entries. Do not add all counts to platform demand totals. DMGT-91 appears in both AF and PF source descriptions, requiring cross-squad scope confirmation before unique-demand reporting. DMGT-56 planned 4 October. PF milestone source also lists it under Oct 2026 achievements, but actual delivery is not confirmed by the September executive summary.

## Slide 10
DIB / CET MONTHLY PERFORMANCE
PF delivery timeline: September 2025–October 2026
Milestone lanes show completed work and the next planned release.
September 2026 • Source: supplied platform and squad reports
10
2025
✓ Completed
✓ Sep 2025
DMGT-90
Disclosure notification in PF STL
›
✓ Oct 2025
DMGT-54: Account start date in LS cases
DMGT-94: FinnOne PF applications for People of Determination
›
✓ Nov 2025
DMGT-1459
New pricing for PF products
2026
✓ Completed
✓ Jan 2026
DMGT-1665
PF rate change
›
✓ Feb 2026
DMGT-81: LC rule change in FinnOne
DMGT-254: PF policy changes
›
✓ Apr 2026
DMGT-105: LL / LG flag field amendment
DMGT-2029: Special employer campaign pricing
DMGT-2065: Frontline employer pricing
2026
✓ Completed
◷ Planned
✓ Jun 2026
DMGT-913: Add employer pricing campaign
DMGT-2231: Additional frontline employer campaign
›
✓ Jul 2026
DMGT-2296
Extend the existing Frontline Hero campaign
›
✓ Aug 2026
DMGT-2407
LS NTML for PF
›
◷ Oct 2026 planned
DMGT-56
FTS in all STL segments
4 October target in September summary
Delivery confirmation pending
Notes: Source: supplied PF milestone and September executive summary attachments. Historical milestone names and IDs are retained. Only supplied months appear. DMGT-56 is shown under October 2026 in the milestone source, but the September summary gives a planned 4 October go-live. Delivery remains unconfirmed. Roadmap lanes group milestones by period and are not scaled to elapsed time.

## Slide 11
DIB / CET MONTHLY PERFORMANCE
CRM delivers 15 items with no reported outages
September executive outcome. Reliability remains green, with a minor-incident workload to monitor.
September 2026 • Source: supplied platform and squad reports
11
35
pipeline entries
15
live / delivered
16
in progress
4
under discussion
✓ Service continuity
0 planned or unplanned outages
0 major incidents
127 minor incidents
DR available and tested
♙ Customer activity
1,242 CIF records
51,525 leads created
45,465 opportunities created
5,544 cases completed
☁ Cloud readiness
Planning / under discussion
Q3 2027 target in latest overview
10 team members
Source reports adequate staffing
Management focus
Track minor-incident drivers, progress the 16 delivery entries and agree the cloud migration approach.
Notes: Source: CRM overview IMG_29BCD58C-7D3B-40A6-96C0-6264C3E77CD5.jpeg and CRM demand-list screenshots IMG_FB9C6BDA-7B1E-4979-9011-8122DC64DB60.jpeg and IMG_EFAC1DEB-A9A4-485C-A801-7EEC6B6B5692.jpeg. Overview 35=15+16+4. Demand list agrees on entry counts: 15 Live,16 In Progress,4 Under discussion. Do not add CRM total to existing platform totals without cross-platform ID deduplication. Source reports team adequacy but supplies no utilization or allocation evidence. Counts are September reporting snapshots, not validated monthly completions. No availability percentage supplied.

## Slide 12
DIB / CET MONTHLY PERFORMANCE
CRM supports customer onboarding and sales activity
Workflow volumes are separate activity measures. Weekly incidents total 127, all minor.
September 2026 • Source: supplied platform and squad reports
12
Weekly minor incidents
Chart: 
| Week 1 | Week 2 | Week 3 | Week 4
Reported volume | 28 | 31 | 34 | 34
Workflow activity
Chart: 
| Cases done | CRAT | GBO | Leads | Opportunities
Reported volume | 5544 | 8382 | 10028 | 51525 | 45465
1,242 CIF records in September
♙ Retail
1,016
◆ Corporate
11
▣ Escrow
1
◉ BBU
214
Notes: Source: CRM overview. Weekly minor incidents 28+31+34+34=127. Week4 versus Week1 is +6 incidents or +21.4%, a within-month comparison only. CIF sum 1016+11+1+214=1242. Retail share81.8%. Workflow categories may overlap and must not be summed as unique customers or transactions. Lead and opportunity counts do not establish a conversion rate or revenue benefit.

## Slide 13
DIB / CET MONTHLY PERFORMANCE
CRM live delivery spans controls and customer workflows
15 live entries: 7 CRM-owned and 8 supporting, as labelled in the demand list.
September 2026 • Source: supplied platform and squad reports
13
✓ CRM-owned delivery (7)
DMGT-1352: CPR bulk personal-data consent
DIBITP-163: CRM data archival setup
DMGT-304: Fax indemnity flag modification
DMGT-719: Auto-closure enhancement
DMGT-1262: Electronic-signature re-push
from CRM / Tablet / Mobile Banking
DMGT-1222: Aggregator sales channel for CRAT
DMGT-1364: Email upon complaint closure
✓ Supporting delivery (8)
DMGT-125: Digital Salam Contract
DMGT-1567: SA-10 additional currencies
DMGT-951: FinnOne PDC automation
DIBITP-2747: Kafka Event Hub upgrade
DMGT-22: Millionaire ESG Saving Account
DMGT-1334: KYC Phase 2
DMGT-929: FATCA / CRS controls
DMGT-1506: 3DS CB Mandate for KONY
Notes: Source: CRM demand list, Live entries. Titles condensed for readability. DMGT-1262 here explicitly denotes electronic-signature re-push in the supplied list, not cloud migration. DMGT-22 source: Millionaire ESG Saving Account, digital channel IB/MB/CRM. Supporting deliveries may also appear in other platform portfolios and must not be added without deduplication.

## Slide 14
DIB / CET MONTHLY PERFORMANCE
CRM execution covers compliance, security and integrations
16 in-progress entries: 9 CRM-owned and 7 supporting.
September 2026 • Source: supplied platform and squad reports
14
⚙ CRM-owned execution (9)
DMGT-1244: Investment Banking onboarding
DMGT-28: CDD / EDD automation for asset IR cases
DMGT-714: Customer 360 statements / blacklist flag
DMGT-1453: Email-to-case conversion
DMGT-1345: HNWI / client class / investment risk
DMGT-976: FinnOne integration with Tesla
DMGT-1980: Staging controls / RTB readiness
DMGT-1406: CPR implementation gap fixes
DMGT-1598: CRM security fix
⚙ Supporting execution (7)
AIG: A-Ignite support
DMGT-1020: Onboarding dedupe controls
DMGT-960: E-Invoice
DMGT-1680: New Emirati Covered Card
DMGT-1842: EFR
DMGT-1272: Five-field input validation
DMGT-1272: Engagement Platform Drop 2 (Unica)
Two different entries share DMGT-1272.
Confirm identity before unique-demand reporting.
Notes: Source: CRM demand-list screenshots. 9 CRM-owned in-progress entries and7 supporting. DMGT-1272 (also written DMGT 1272) appears twice with distinct titles: Input Validations - Channels/platforms (Individuals) - Five Fields, and Engagement Platform Drop2 (unica). Keep35 row-based pipeline entries until duplication is resolved. Source DMGT-1980 title CRM Staging Environment Control & RTB Readiness. Source DMGT-1406 CPR Personal Data Consent Management analyzing and fixing implementation gaps/issues.

## Slide 15
DIB / CET MONTHLY PERFORMANCE
CRM cloud migration needs a defined execution approach
Latest overview targets Q3 2027. The demand list records cloud migration as under discussion.
September 2026 • Source: supplied platform and squad reports
15
◉ Now
Planning / discussion
Agree scope, dependencies
and migration approach
›
⚙ Preparation
Readiness work
Define recovery, testing
and cutover acceptance
›
☁ Q3 2027
Source target
Prepare for execution
Confirm baseline and dates
Four entries under discussion
☁ DMGT-710
CRM migration to cloud
✉ DMGT-1154
Complaint management transformation
◉ DMGT-2336
Fraud / dispute workflows
Accounts and cards
↗ DMGT-752
Remittance workflow automation
Notes: Source: latest CRM overview cloud migration target Q3 2027, planning status. Demand list DMGT-710 under discussion. Preparation tasks and acceptance evidence are management recommendations, not source-approved milestones. All four under-discussion entries preserved. Source also assigns DMGT-1262 to a live electronic-signature item; this deck uses current attachment identifiers and does not reuse earlier memory associations.

## Slide 16
DIB / CET MONTHLY PERFORMANCE
Call centre: September abandonment needs attention
Interactive review. Click a coloured topic box to open its detail slide.
September 2026 • Source: supplied platform and squad reports
16
446,482
September IVR calls
68.45%
IVR completion
11.77%
call abandonment
78 / 81
incidents closed
☎ Service trends
Jan–Sep demand and service outcomes
✓ Service controls
Incidents, SLA and authentication
▦ IVR transactions
Self-service activity by function
♙ Agent licences
Daily usage and capacity evidence
☁ Own initiatives
Five demands and cloud roadmap
↗ Supporting portfolio
Thirteen demands across partner teams
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. September IVR completion increased by0.46 percentage points versus August, while call abandonment increased4.31pp. Jan–Sep overall rates69%completion31%agent transfer92%answered8%abandoned are separate source summary measures. Source September dashboard rounds to68%containment32%transfer88%answered12%abandoned. Navigation is implemented with slide hyperlinks and no entrance effects.

## Slide 17
DIB / CET MONTHLY PERFORMANCE
IVR completion improved slightly as abandonment rose
September versus August: completion +0.46 percentage points, abandonment +4.31 points.
September 2026 • Source: supplied platform and squad reports
17
IVR completion
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Completion | 70.03 | 70.39 | 69.7 | 70.64 | 70.08 | 68.95 | 67.83 | 67.99 | 68.45
Call abandonment
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Abandonment | 9.83 | 8.75 | 15.33 | 5.31 | 4.32 | 5.03 | 7.03 | 7.46 | 11.77
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Reported volume | 451254 | 394343 | 416078 | 454112 | 441931 | 438815 | 454393 | 423787 | 446482
3.92M IVR calls, Jan–Sep
435,117 average per month
Peak: July, 454,393
Lowest: February, 394,343
Jan–Sep: 69% completion, 31% transfer. Agent outcomes: 92% answered, 8% abandoned.
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. September call count446482 comes from September dashboard because the monthly trend label is obscured. Monthly values sum3916195 and average435132.8; supplied summary average435117 differs slightly. Retain reported avg and flag reconciliation rather than overwrite it. Jan–Sep source3.92M rounded. Percent charts use percentage numbers70.03 not0.7003. No causal attribution supplied for abandonment changes.

## Slide 18
DIB / CET MONTHLY PERFORMANCE
Call-centre incidents remain within the reported SLA
81 incidents: 78 closed and 3 in progress. No P1 or P2 incidents reported.
September 2026 • Source: supplied platform and squad reports
18
81 / 81
within reported SLA
0
exceeded SLA
73
P3 incidents
8
P4 incidents
☎ September call flow
446,482 IVR calls
68% containment / 32% agent transfer
146,785 agent calls
88% answered / 12% abandoned
Source rates are rounded
✓ Identification and verification
69% customer identification
25% TPIN verified
7% biometrics verified
Measures may use different denominators.
Treat them as separate rates.
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. Source81withinSLA0exceed does not state treatment of3openincidents. Avoid inferring all open incidents resolved.78/81=96.3%closed3/81=3.7%open, dashboard rounds96/4. No P1 or P2, P3 73,P4 8. IVR agent transfer and agent-call totals need not share scope, so do not force reconciliation or sum call counts.

## Slide 19
DIB / CET MONTHLY PERFORMANCE
TPIN and card activation dominate IVR transaction activity
Source activity counts describe functions, rather than unique callers.
September 2026 • Source: supplied platform and squad reports
19
Chart: 
| Utility payments | Etisalat payments | DU payments | Salik payment | Funds transfer | Cheque-book request | Cash on card | Card payment | Change card PIN
IVR transactions | 388 | 1371 | 238 | 115 | 1863 | 495 | 3 | 114 | 181
Change card PIN
Card payment
Cash on card
Cheque-book request
Funds transfer
Salik payment
DU payments
Etisalat payments
Utility payments
Chart: 
| Last 5 card transactions | Activate card | Reset card PIN | Lost / stolen card | Reset TPIN | Block TPIN | Generate TPIN | Change TPIN
IVR transactions | 1030 | 13337 | 4752 | 294 | 18146 | 12004 | 5871 | 456
Change TPIN
Generate TPIN
Block TPIN
Reset TPIN
Lost / stolen card
Reset card PIN
Activate card
Last 5 card transactions
Top functions: Reset TPIN 18,146; Activate card 13,337; Block TPIN 12,004.
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. All17activity counts transcribed from September dashboard. No unique-customer denominator supplied. Source spelling Card Last5Trans retained as Last5cardtransactions. Do not label transaction totals as revenue or uniquecalls.

## Slide 20
DIB / CET MONTHLY PERFORMANCE
Daily agent-licence usage peaks at 492
The source reports 100% overall licence usage but does not supply a licensed capacity denominator.
September 2026 • Source: supplied platform and squad reports
20
Chart: 
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Agent licences | 427 | 391 | 418 | 430 | 328 | 72 | 427 | 432 | 433 | 427 | 427 | 336 | 106 | 477 | 426 | 457 | 457 | 440 | 303 | 93 | 441 | 433 | 486 | 492 | 468 | 341 | 74 | 442 | 447 | 432
492
peak on 24 September
72
low on 6 September
432
30 September count
100%
source overall usage
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. All30dailyvalues transcribed. Weekendlows exist but no staffing schedule is supplied, so causes are not asserted. Peak492min72end432. 100%overallusage is source-reported and undefined, cannot infer saturation, concurrent licensingcapacity or shortage. Management recommendation: confirm denominator and peak capacity buffer.

## Slide 21
DIB / CET MONTHLY PERFORMANCE
Call-centre portfolio: two closures and two reviews
Five own demands. Suspension and review require explicit management decisions.
September 2026 • Source: supplied platform and squad reports
21
✓ DMGT-2171
IVR WhatsApp / SMS extension
Closure
September 2026 go-live
✓ DMGT-443
Eleveo recording OS remediation
Closure
July 2026 go-live
☁ DMGT-1837
Call Centre cloud migration
Review
Q4 2027 target
▦ DMGT-2147
Recording / reporting for telemarketing regulations
Review
Go-live TBD
Ⅱ DMGT-250
IVR WhatsApp / SMS notifications
Suspended
April 2026 source date
◉ Review priorities
Confirm suspended demand disposition
Agree review outcomes and dates
Maintain cloud migration readiness
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. Own demand AE Lead CT.250 platformenrichment suspended Apr26 date is reported not proof of delivered status;2171 platformenrichment closure Sep26;443 resiliency closure Jul26;1837 resiliency reviewQ42027;2147 enrichment reviewTBD. Sourceclosure statuses are not re-labelled as new September completions.

## Slide 22
DIB / CET MONTHLY PERFORMANCE
Partner support spans 13 demands across CET, CORE and EIS
Five fulfilled, five in support, two in review and one not approved.
September 2026 • Source: supplied platform and squad reports
22
✓ Fulfilled (5)
1692: DIB logo update (CET), Feb 2026
22: ESG digital savings (CET), Jul 2026
1707: DNCR API / Genesys testing (EIS), Sep
993: Jaywan Tracks 2 & 3 (CET), Sep
43: Deposit-account credit restrictions (CORE)
⚙ In support (5)
1368: DU ePayment (CET)
1326: Dormancy / fund transfer to CBUAE (CORE)
714: Statements / blacklist flag (CORE)
1680: Emirati covered cards (CET)
1305: Jaywan CoBadge Track 4 (CET)
◉ Decisions (3)
1802: Universal Accounts
Notice 680.2026 (CET), ITC review
1248: Collections dialer upgrade
(EIS), ITC review
1785: A-Ignite engagement / dialer
(CET), ITC not approved on 21 Sep
↩ Call-centre overview
Notes: Sources: September Call Center Projects Dashboard IMG_047BD122-E741-4EF7-B317-D2B79DE72B1A.jpeg; Jan–Sep Performance Review IMG_B0166ECF-764F-4E01-A8DC-B0B5CD7B8B73.jpeg; September Platform Dashboard IMG_5353CD62-9824-4F23-84B9-330C231D8C5D.jpeg. AllnumericIDs useDMGTprefix. No closuredate supplied for43. Demand types from source:1692improvedcontrols,22serviceenhancements,1707improvedcontrols,993platformenrichment,43improvedcontrols,1368serviceenhancements,1326improvedcontrols,714serviceenhancements,1680serviceenhancements,1305platformenrichment,1802serviceenhancements,1785serviceenhancements,1248serviceenhancements. Supporting IDs may duplicate other platform sections. Do not sum as enterpriseunique demands.

## Slide 23
DIB / CET MONTHLY PERFORMANCE
CCM/SMS, ATM and resiliency: executive outcome
September operating results and the next management decisions
September 2026 • Source: supplied platform and squad reports
23
30 / 48
CCM/SMS delivered
6 / 13
ATM delivered
515 / 530
ATM XFS rollout
8
resiliency platforms
✉ CCM/SMS
71.10M reported email and SMS events
Zero reported incidents or outages
CCM has no DR
SMS DR available and tested
▣ ATM
4.016B ATM transaction amount
1 critical and 7 major incidents
KAL DR test completed in August
Memory reaches 90.2% on one host
◆ Resiliency programme
Six staging environments denied
IB / Omni shift proposed to Q2 2027
Council items need closure evidence
Delivery gates need agreed owners
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. CCM/SMS delivered30=18platform+12support, total48. ATM delivered6=4platform+2support, total13. Do not add as enterprise unique demands because supporting IDs may overlap. CCM email30732241+SMS40366362=71098603 events, not unique customers. XFS515/530=97.17%. Amount currency unspecified. Executive recommendations, not approved decisions.

## Slide 24
DIB / CET MONTHLY PERFORMANCE
CCM/SMS delivered 30 of 48 reported demands
Jan–September portfolio snapshot. Sixteen demands remain in progress and two in B0 discussion.
September 2026 • Source: supplied platform and squad reports
24
Chart: 
| Delivered | In progress | B0 discussion | Backlog
Reported volume | 30 | 16 | 2 | 0
✓ Delivered: 62.5%
Platform 18 / Supporting 12
SMS Retail Banking Upgrade
EKYC AN/DN
⚙ Remaining delivery
Platform 2 / Supporting 14 in progress
CCM Release 17 in pipeline
Sitefinity website upgrade in planning
e& services consolidation in planning
SMS Corporate upgrade in execution
Resiliency remediations are in execution across the platforms.
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Snapshot share30/48=62.5%,16/48=33.3%,2/48=4.2%. No monthly throughput inference. Source calls discussion B0. Strategic initiative CCM Upgrade Rel17, website latestSitefinity,e&servicesconsolidation,resiliencyremediations,SMSCorporatebankingupgrade. No individual demandIDs supplied.

## Slide 25
DIB / CET MONTHLY PERFORMANCE
CCM/SMS processes 71.10M reported events
September throughput remains outage-free, with different recovery capabilities across the two platforms.
September 2026 • Source: supplied platform and squad reports
25
Chart: 
| CCM email | SMS transactions
Reported volume | 30.7322 | 40.3664
✉ CCM
CPU 4.14–6.45%
Memory 34.3–44.7%
HA at Site 1
DR unavailable and untested
☏ SMS
CPU 0.608–2.98%
Memory 20.5–35.4%
DR available and tested
Site 2 activation / Q1 2027 drill planned
0 incidents 0 outages 0 minutes downtime
Storage figures need reconciliation before capacity decisions.
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Capacity screenshot CCMCPU6.45/4.14 memory34.3/44.7. SMSCPU2.98/2.33/.608/.640 memory35.4/31.7/21.8/20.5. CCMstorage11.1TB/14TB with60.5%, arithmetic79.3%. SMS2.1TB/14TB withlabel7.9TB%, arithmetic15%. Inconsistent percentages retained only in notes, no invented corrected source utilization. Availability~100%, both planned/unplannedoutages0downtime0. SMS DRtestedyes fromreliabilityslide and nextdrillQ12027 fromcapacityslide. Source subtitle generictestedDR doesnotapplyCCM.

## Slide 26
DIB / CET MONTHLY PERFORMANCE
ATM rollout reaches 515 of 530 terminals
Thirteen reported demands: six delivered, four in progress and three in B0 discussion.
September 2026 • Source: supplied platform and squad reports
26
Chart: 
| Delivered | In progress | B0 discussion
Reported volume | 6 | 4 | 3
XFS upgrade: 15 terminals remain
97.2%
▣ Delivery and rollout
4 platform / 2 supporting demands delivered
33 replacement ATM machines
Smart CDM: Brinks & TG completed
TLS update completed, rollout plan in progress
⚙ Strategic initiatives
NBV SaaS upgrade: in progress
Board decision pending
KTC upgrade: planning within resiliency
XFS upgrade: rollout in progress
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. ATMtotal13 delivered4/2,progress1/3,backlog0,B0discussion3. Snapshotdelivery46.15%,progress30.77%,discussion23.08%. XFS515/530 source completed,97.17% derived. NBVsourceBoardvantage. TLSsource completed withrolloutplaninprogress, donotassertallterminalsrolledout.

## Slide 27
DIB / CET MONTHLY PERFORMANCE
ATM/CDM activity carries material operational risk
Reported near-100% availability coexists with eight incidents in September.
September 2026 • Source: supplied platform and squad reports
27
2.22M
ATM transactions
339,585
CDM transactions
4.016B
ATM amount
1.223B
CDM amount
! Incident profile
1 critical: cheque-image processing
7 major incidents
No reported unplanned outages
0 minutes reported downtime
◆ Recovery position
DR available and tested
KAL test: 22 August 2026
Next reported activity: Q1 2027
Recovery evidence needs a defined scope
▤ Cheque-image remediation
CDM images retransmitted to KTC
Envelope-file creation for ICCS
Management review should confirm completion and affected-item reconciliation
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Source dailyaveragesATM76628CDM11709 do not reconcile with rounded totals over30days, appear29daybasis. Display totals and preserve daily averages in notes without inventing denominator. Currency unspecified. Nextactivity tile saysPlannedQ12027 withoutactivitylabel. DRtestAugust22source. Incidents neednotproduceoutage. Near100availability doesnotprove zero customer impact. Recommendationsidentifiedasmanagementreview.

## Slide 28
DIB / CET MONTHLY PERFORMANCE
ATM memory is concentrated on three KAL hosts
Peak CPU is 10.5%, while KAL database hosts report memory utilization above 86%.
September 2026 • Source: supplied platform and squad reports
28
Chart: 
| kala1 | kala2 | kalw1 | kalw2 | kald2 | kald3 | dxb02 kald1
Reported volume | 37.5 | 30.4 | 29 | 28.4 | 90.2 | 87.2 | 86.3
▦ Capacity watch
kald2 memory: 90.2%
kald3 memory: 87.2%
dxb02 kald1: 86.3%
Storage peak: 76.4%
◉ Recommended review
Check memory trend and workload
Confirm alert thresholds
Validate headroom during failover
Assign remediation if needed
Memory utilization by host
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Hosts abbreviated for readability. All dib.ae: dxb01-vwp-kala1,kala2,kalw1,kalw2,kald2,kald3 and dxb02-vwp-kald1. CPU3.90,2.01,3.69,1.79,10.5,2.60,1.36%. Memory37.5,30.4,29,28.4,90.2,87.2,86.3%. Storage46.2,59.3,34.3,51.2,76.4,75.3,44.9%. No approved utilization threshold supplied, so do not label actual breach or capacity exhaustion.

## Slide 29
DIB / CET MONTHLY PERFORMANCE
Technology Oversight Council: ten tracked items
The source rates eight items Rare and two Frequent. Ratings describe probability, not severity.
September 2026 • Source: supplied platform and squad reports
29
10
tracked council items
2
Frequent probability
8
Rare probability
24 Oct
KAL rollout target
! Frequent: KAL device observability
Three production pilot terminals
EID-device status fix under monitoring
Rollout planned from 4 to 24 October 2026
Closure needs rollout and monitoring evidence
! Frequent: online duplicate transfers
Future-dated DFT / IFT duplicate transactions
Development in progress
EFMS Release 1 target: December 2026
Closure needs transaction-control evidence
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. TOCsource rows1–10, rare8 frequent2. Probabilitynotriskseverity. October4and24remainplannedsource dates, noactualreleaseconfirmation supplied even though currentdateafterOct4. Eightotheritems in nexttwo slides. DatesQ22007 in source flagged, no silentcorrection.

## Slide 30
DIB / CET MONTHLY PERFORMANCE
Council control actions: notifications and security
Planned releases and fixes need evidence before the council records closure.
September 2026 • Source: supplied platform and squad reports
30
✉ SMS duplicate notifications
Debit / credit, ATM and Power Card alerts
Source planned release: 4 October 2026
Actual deployment confirmation required
Probability: Rare
◆ SMS OTP masking
Centralize templates from SOA, IB and MB
Demand created with DAMO team
Payload and template redesign required
Probability: Rare
▣ Website exchange interface
Plain-text-password fix deployed
Further findings / requirements pending
Closure needs remaining scope confirmed
Probability: Rare
☎ Call-centre support lifecycle
VHT support ended December 2023
Genesys DataMart support ended May 2021
Addressed within call-centre upgrade
Probability: Rare
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Councilrows1SMSduplicate,2OTPunmasked,4website,6callcentre. Recommendationsclosureevidence notsource commitment. Websitefixonlyexchangeinterface, notallfindings. OTPdemandIDs/datesnotprovided.

## Slide 31
DIB / CET MONTHLY PERFORMANCE
Council modernization actions span four platforms
Legacy technology and incomplete journey visibility remain on the council agenda.
September 2026 • Source: supplied platform and squad reports
31
▣ Power Card
Latency, EOD delays and CMS v2 / Switch v3 sync
HPS engagement for a two-week review
Replacement under management directive
Probability: Rare
◉ Mobile journey tracking
PF / CC journey tracking implemented
PF squad enhancements in progress
RtB reports only raw logs, limiting business visibility
Dynatrace exploration proposed. Probability: Rare
☁ OMNI / Internet Banking
Unsupported technology stack
Upgrade within the resiliency programme
Scope proposes IB / Omni for Q2 2027
Probability: Rare
◆ HFLMS
Unsupported stack and no HA / DR in council report
Platform upgrade in progress
Scope table targets Q4 2026
Council target year requires confirmation
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Councilrows5,7,9,10. Row7and10 targetsprintedQ22007 invalidrelative2026report. Preserveflag, donotsilentlyturn2027. OMNIIBscopeproposesQ22027forcapacity. HFLMSscopeQ426 differscounciltarget. JourneytrackingstatusclaimsimplementedPFCC butRtBnoteonlyrawdatawhichdoesnothelpbusiness. Slide paraphrase mustshow conflictnotclaimcomplete visibility.

## Slide 32
DIB / CET MONTHLY PERFORMANCE
CET resiliency strategy covers eight platforms
Programme scope combines legacy upgrades, database resilience and recovery architecture.
September 2026 • Source: supplied platform and squad reports
32
✉ Ducont SMS
Ramzi Rizvan
◆ HFLMS
Naveed Rashid
★ ICC Loyalty
Ebrahim
▦ Direct Equity / Matrix
Ramzi Rizvan
▣ KAL System
Ramzi Rizvan
◉ DIB Website
Ramzi Rizvan
☏ Mobile App / Omni
Naveed Rashid
⌂ Internet Banking
Naveed Rashid
⚙ Operating-system modernization
Windows / SQL upgrades to 2022 across the stated scope
◆ Recovery architecture
HA / DR and Always On designs differ by platform
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Owners exactlyfromscope RamziRizvan,NaveedRashid,Ebrahim. Eightplatforms fourBSR fourOD. Scopeisplannedprogramme, notcompletionevidence. Budgets,migrationchecklistandreleaseworkflowmentionedincoverbutnotprovided. No inventedcostRTO/RPOorcompletion.

## Slide 33
DIB / CET MONTHLY PERFORMANCE
Resiliency roadmap: four platforms target Q4 2026
IB and Omni have a proposed shift from Q1 to Q2 2027 because of team capacity.
September 2026 • Source: supplied platform and squad reports
33
Q4 2026
Scope-table targets
Ducont SMS
HFLMS
ICC Loyalty
Direct Equity / Matrix
›
Q1 2027
Scope-table targets
KAL System
DIB Website
Milestones require a confirmed delivery baseline
›
Q2 2027
Proposed timing
Mobile App / Omni
Internet Banking
Original scope table: Q1 2027
◷ Capacity dependency
Critical Q1 commitments include CBUAE notice 3057. Revised IB / Omni dates remain proposed.
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Scope allfirst4Q426 next4Q127. FootnotesaysInternetBankingOmniproposedQ22027becausecapacityincriticalQ1projectsCBUAEnotice3057. ThisisaquarterlaneroadmapnotdurationGantt. HFLMSQ426scopeconflictsTOCQ22007and earlierportfolio2027DRupgrade, needsbaselineconfirmation.

## Slide 34
DIB / CET MONTHLY PERFORMANCE
Recovery designs differ across the eight platforms
The scope defines architecture changes, rather than achieved recovery capability.
September 2026 • Source: supplied platform and squad reports
34
◆ Active-active HA / DR
Ducont SMS
SMS / CCM database segregation
Windows and SQL 2022
Database Always On (3+2)
DIB Website
Active-active architecture
Windows and SQL 2022
Mobile App / Omni
Application OS 2012 to 2022
▦ Database and passive DR
HFLMS
Application OS 2012 to 2022
Passive DR setup
Database Always On (2+1)
KAL System
Web / application OS 2022
SQL / OS 2022, Always On (3+2)
Internet Banking
Web / application OS 2022
SQL 2022, Always On (3+2)
⚙ Legacy stack upgrades
ICC Loyalty
Windows 2012 to 2022
SQL 2014 to 2022
Direct Equity / Matrix
Application OS 2012 to 2022
SQL / OS 2016 to 2022
RTO / RPO and test acceptance criteria are not supplied.
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Exactsource scope retained. Activeactivedesignisproposed, nottestedstatus. HFLMSpassiveDRscope. KALandIB3+2AlwaysOnsource. ICCandMatrixnotspecificallyactiveactiveinscope. Recommendedgatesnextslide notnewsourcefacts.

## Slide 35
DIB / CET MONTHLY PERFORMANCE
Provisioning confirms UAT and production for all eight
Six platforms have denied staging provisioning. Green means infrastructure confirmation, not release readiness.
September 2026 • Source: supplied platform and squad reports
35
Platform
SIT
UAT
Staging
Production
DR
IB
×
✓
×
✓
◉ Passive
Omni
×
✓
×
✓
✓
DIB Website
NA
✓
×
✓
✓
SMS (DB cluster)
NA
✓
×
✓
✓
HFLMS
×
✓
×
✓
◉ Passive
Matrix (Tier 4)
NA
✓
NA
✓
◉ Passive
ICC Loyalty (DB)
NA
✓
NA
✓
◉ Passive
KAL
NA
✓
×
✓
◉ Passive
✓ Confirmed × Denied ◉ Passive DR NA Not applicable
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Environmentmatrixsource exact8rows. UATproduction8confirmed. Staging6denied2NA. SIT3denied5NA. DR3greenconfirmedOmniWebsiteSMS,5passiveIBHFLMSMatrixICCKAL. ProvisioningisnotdeployedtestedDR. No contradictionresolve withcurrentHFLMSnodr. Requirementtoexplaindifference visible.

## Slide 36
DIB / CET MONTHLY PERFORMANCE
Resiliency infrastructure: website, SMS, HFLMS and loyalty
Source server totals include requested environments. Staging entries appear as provisioning denied.
September 2026 • Source: supplied platform and squad reports
36
DIB Website 26 servers
NP / STG / PROD / DR
Application: 1 / 3 / 3 / 3
Database: 1 / 3 / 3 / 2
Web: 1 / 2 / 2 / 2
Storage total: 6,768
Ducont SMS 12 servers
NP / STG / PROD / DR
Application: 1 / 2 / – / –
Database: 1 / 3 / 3 / 2
Storage total: 13,550
Programme scope: DB cluster
HFLMS 19 servers
NP / STG / PROD / DR
Application: 2 / 2 / – / 5
Database: 2 / 3 / 3 / 2
Storage total: 40,226
ICC Loyalty 3 servers
NP / STG / PROD / DR
Database: 1 / – / 1 / 1
Storage total: 6,648
Programme scope: DB only
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Infrastructure source footer totals. DucontSMSfooter13,550. Storageunitsnotlabelled,notassumedGB/TB. TotalsincludingdeniedSTGarenotapprovedprovisionedcapacity. DIBWebsiteapp1,3,3,3 db1,3,3,2 web1,2,2,2. SMSapp1,2,dash,dashdb1,3,3,2. HFLMSapp2,2,dash,5db2,3,3,2. ICCdb1,dash,1,1. Source detailedstorage numbers shouldbereconciledwithfooterbeforeaggregation.

## Slide 37
DIB / CET MONTHLY PERFORMANCE
Resiliency infrastructure: IB, KAL, Matrix and Omni
Infrastructure design quantities remain separate from operational platform health measures.
September 2026 • Source: supplied platform and squad reports
37
Internet Banking 42 servers
NP / STG / PROD / DR
Application: 6 / 4 / 5 / 5
Database: 3 / 3 / 3 / 2
Web: 3 / 2 / 3 / 3
Storage total: 34,958
KAL 23 servers
NP / STG / PROD / DR
Application: 1 / 2 / 2 / 2
Database: 1 / 3 / 3 / 2
Web: 1 / 2 / 2 / 2
Storage total: 12,808
Matrix 6 servers
NP / STG / PROD / DR
Application: 1 / – / 1 / 1
Database: 1 / – / 1 / 1
Storage total: 10,530
Mobile App / Omni 11 servers
NP / STG / PROD / DR
Application: 2 / 3 / 3 / 3
Storage total: 2,498
Staging provisioning denied
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Source infrastructurefooterIB42storage34958,KAL23storage12808,Matrix6storage10530,Omni11storage2498. Unitsunspecified. All8source servertotals sum142 includesrequesteddeniedSTG and maynotmeanphysicaluniqueservers. Noapprovedcostorbudget. NPsourceheadingnotautomaticallySIT. Servercountseditable. Storagecomponent arithmetic notvalidated against totals.

## Slide 38
DIB / CET MONTHLY PERFORMANCE
Management decisions and evidence for the next review
Recommended governance gates for the new platform and resiliency sections
September 2026 • Source: supplied platform and squad reports
38
1 Release baseline
Confirm IB / Omni proposed Q2 2027 dates
Reconcile HFLMS Q4 2026 scope with 2027 DR plan
Correct council entries that show Q2 2007
Confirm 4 October releases with actual evidence
2 Environment approval
Resolve six denied staging requirements
Document alternatives and accountable approvals
Confirm passive DR provisioning versus operational capability
3 Recovery acceptance
Agree platform RTO / RPO and test criteria
Track failover, failback and data integrity evidence
Assign owners for CCM DR and SMS Site 2
Define production release acceptance
4 Capacity and reporting
Review ATM memory trends and failover headroom
Reconcile CCM/SMS storage figures
Confirm infrastructure quantities and storage units
Budget / migration checklist not supplied
Notes: Sources: supplied CCM/SMS, ATM, Technology Oversight Council and CET Resiliency Strategy screenshots, September 2026. Allfourcardsareanalyticalrecommendations, notapprovedplan. Noexternalbenchmarkintroduced. Remainingcover-onlytopicsmigrationchecklistbudgetandproduction/nonproductionworkflowswerenotsuppliedandarenotinvented. Infrastructurequantitiessourcefooterneedreconciliation. CurrentversusplannedDRdistinguished.

## Slide 39
DIB / CET MONTHLY PERFORMANCE
Cards portfolio: delivery continues, with capacity on watch
September 2026 executive outcome. Source health status: Green.
September 2026 • Source: supplied platform and squad reports
39
58
reported delivered
39
in progress
78.6%
transaction success
99.9%
availability
▣ Business activity
1.35M active credit and debit cards
22,820 new cards reported in September
30.89M transactions / 24.29M successful
No critical incidents, 3 major incidents
◉ Management focus
Memory utilization: 94.5% average
Demand counts need reconciliation
Three named demands are in UAT
VAU stage differs across the attachments
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. Activecards347156credit+1003169debit=1350325. New9576credit+13244debit=22820. Reporteddemandtotal147 butfivestatuscounts137 andsupporting20 yield157ifadded. Do notforcecategorysharesorenterpriseaggregation. Illustrationontransactions slideisgeneratedunbrandedconcept, notrealDIBcard.

## Slide 40
DIB / CET MONTHLY PERFORMANCE
Cards demand counts require reconciliation
The report states 147 total demands. Five delivery-state counts sum to 137.
September 2026 • Source: supplied platform and squad reports
40
Chart: 
| Delivered | In progress | New demand | Backlog | Dropped / hold
Reported volume | 58 | 39 | 9 | 17 | 14
▦ Supporting: 20
Treat supporting involvement as a separate measure until overlap is confirmed.
! Reconciliation needed
Five states: 137
Including supporting: 157
Reported total: 147
Confirm classification and demand IDs before using a composition chart.
Execution focus: 39 in progress, 17 backlog and 9 new demands.
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. Sourcecounts58+39+9+17+14=137. Adding20supporting=157 ratherthan147. Originaldonutpercentages39+27+6+12+10+14=108%; no validcompositionreproduced. Source39%delivered isrounded58/147 but denominatorneedsconfirmation. We preserveallcountsandavoidimpliedmutuallyexclusivestates. Dropped/onholdcannotbesplitwithprovideddata. Noage,priorperiodoruniquelistprovided.

## Slide 41
DIB / CET MONTHLY PERFORMANCE
Cards transaction success is reported at 78.6%
September counts show a 6.60M difference between total and successful transactions.
September 2026 • Source: supplied platform and squad reports
41
Chart: 
| Total transactions | Successful
Reported volume | 30.89 | 24.29
◉ Outcome review
The remaining 21.4% needs outcome classification. The source does not identify declines, reversals or technical failures.
▣ Active cards
Credit: 347,156
Debit: 1,003,169
New credit: 9,576
New debit: 13,244
Illustrative card concept
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. Totalandsuccessfultransactionvolumemeancountsinmillions, notcurrency. Success24.29/30.89=78.6339% rounded78.6. Difference6.60M21.366%; notnecessarilytechnicalfailures. Noattemptdenominator,declinecodes,duplicatehandlingorreversaldefinitionprovided. Activeandnewcardcountsretainedexact. Newcardsnotnetgrowthwithoutclosures/priorstock. Imagegeneratedforpresentation,noDIBorVisaidentity.

## Slide 42
DIB / CET MONTHLY PERFORMANCE
Cards memory utilization is the main capacity watch
Availability remains 99.9%, with DR available and tested according to the source.
September 2026 • Source: supplied platform and squad reports
42
Chart: 
| CPU | Memory | Storage
Reported volume | 16.5 | 94.5 | 49.3
▦ Host-level follow-up
Memory watch: pcsd1 / pcsd2. Storage watch: DB / ORACLE volumes. Averages can conceal concentrated utilization.
! Incident profile
343 total incidents
0 critical / 3 major
Major share: 0.9%
Other severities not specified
✓ Service continuity
No major service interruptions reported
Monitoring and alerting in place
Close the 3 major root causes
Validate capacity during failover
Source says headroom is available
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. CPU16.50OKcontrolledaverage, memory94.50WATCHpcsd1/pcsd2high,storage49.30WATCHDB/ORACLEvolumeshigh. Nohostspecificpercentagesorapprovedthresholdsupplied. Sourceclaimheadroomavailablecoexistswith94.5memorywatch. 3/343=.8746%=.9%. Remaining340classificationnotprovided, notallminorassumed. Availability99.9,DRyes tested. NooutagenumberorDRtestdateprovided. AnalyticalrecommendationscloseRCAandvalidatefailovercapacity.

## Slide 43
DIB / CET MONTHLY PERFORMANCE
Cards strategic initiatives: seven named demands
Delivery lanes show reported stages. No go-live dates were supplied for this list.
September 2026 • Source: supplied platform and squad reports
43
◷ Planning / design
DMGT-2010
New Chip Migration
Planning / Costing
DMGT-1474
Click To Pay
Solution Design
◆ UAT
DMGT-1680: Emirati Card
DMGT-1979: Jaywan Mono Badge Debit Card
E-commerce / tokenized integration
DMGT-1978: Jaywan E-commerce and Tokenization
TLCM Portal Access
✓ Pilot / release prep
DMGT-1356
VAU: Visa Account Update
Pilot Phase
DMGT-2496
Visa October Enhancements-26
Staging / Go-Live Preparation
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. ExactstrategiclistIDs1680,2496,1356,2010,1474,1979,1978. SourceStaggingnormalizedStaging. VAUnameinlistVisaAccountUpdate;dashboardVisaAccountupdater. Stagesnotplannedtimeorprogresspercent. Sevenselecteditemsnotfull39inprogress. UAT3,planning/cost1,design1,pilot1,staging/go-liveprep1. Noapproveddates/costsprovided.

## Slide 44
DIB / CET MONTHLY PERFORMANCE
Additional card initiatives span release prep and live delivery
The dashboard and named-demand list use different VAU stage labels.
September 2026 • Source: supplied platform and squad reports
44
✓ Go-live preparation
Supplementary Card mobile number / email capture
VAU: Visa Account Updater
Migration from Edit Package to Visa Clearing Exchange (VCX)
⚙ Other dashboard stages
Live: Digital Salam Renewal for Covered Cards
PGL fix deployed
UAT: Covered Card Statement Generation SMS
Development: Jaywan Visa Co-Badged Debit Cards
! VAU stage reconciliation
Dashboard: go-live preparation
Named list, DMGT-1356: pilot phase
Confirm the current stage and release scope.
◉ Next management review
Confirm UAT acceptance and release readiness
Track memory remediation and major-incident closure
Reconcile demand classification before portfolio aggregation
Notes: Sources: Cards Executive Portfolio September 2026, IMG_698C571D-C7E1-4F9B-AB5A-646620DF822D.jpeg; strategic initiative list IMG_2C018236-D2BC-4F45-B5AF-9AFF22498AF4.jpeg. Dashboard6initiative names/statusesretained. Live DigitalSalamRenewalforCoveredCards,PGLfixdeployed. NoIDsprovided forthesixdashboardentriesexceptVAUmatchedbynamewithsecondlist. Do notassumeSupplementaryCardID,JaywanCoBadgeandMonoBadgearethesame,orUATstatementSMSsameasEmirati. Not13uniqueinitiativesdueoverlapVAUandpotentialothers. Noexternalclaimsorapprovaladded. Recommendationsdefinedasnextreview.