## Slide 1
CARDS PORTFOLIO 2026
From portfolio demand
to customer delivery
56 demands with 25 completed and seven planned go-lives through January 2027
25
DELIVERED
23 SEPTEMBER 2026
PROTECT
Secure delivery and controls
BUILD
Portfolio execution and capability
FLOURISH
Customer journeys and propositions
01
Notes: SOURCE: IMG_8CF6D7E4-E31F-4C6C-9E8E-7E059150168F.jpeg and IMG_9453F031-49AD-4FB5-A10C-0BBC67F65DBF.jpeg; IT strategy mapping from the user's DIB CET IT Strategy deck.
VERIFIED: 56 total demands; 25 completed; seven planned go-lives through January 2027. IT strategy pillars are Protect, Build and Flourish.
DERIVED: None displayed.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Protect / Build / Flourish.
NARRATIVE: This presentation follows the Cards portfolio from demand mix and delivery volume into project outcomes, control delivery and the confirmed release plan.

## Slide 2
CARDS PORTFOLIO
BUILD
25 demands delivered across a 56-demand Cards portfolio
Consolidated portfolio position at 23 September 2026
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
02
25
COMPLETED
45% of the portfolio
The portfolio combines completed delivery with 24 demands in Baseline 0 or 1 and seven under discussion.
24
ACTIVE BASELINE
15 B1 + 9 B0
7
UNDER DISCUSSION
Technology review
32
GO-LIVES TRACKED
25 completed + 7 planned
PORTFOLIO LIFECYCLE
25
15
9
7
Completed 25
Baseline 1 15
Baseline 0 9
Under discussion 7
56
TOTAL DEMANDS
Notes: SOURCE: IMG_8CF6D7E4-E31F-4C6C-9E8E-7E059150168F.jpeg and IMG_9453F031-49AD-4FB5-A10C-0BBC67F65DBF.jpeg.
VERIFIED: 56 total demands; 25 completed; 15 Baseline 1; 9 Baseline 0; 7 under discussion; 32 total go-lives; 25 completed go-lives; 7 planned go-lives.
DERIVED: 45% completed is 25 divided by 56, rounded to the nearest whole percentage. Active baseline demand is 15 plus 9, equal to 24.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: The opening slide establishes delivery achieved, the active pipeline and the go-live scale in one view.

## Slide 3
PORTFOLIO COMPOSITION
BUILD
Completed delivery represents 45% of the portfolio
Status distribution and demand origin
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
03
STATUS MIX
Completed
25
Baseline 1
15
Baseline 0
9
Under discussion
7
24 demands remain in Baseline 0 or Baseline 1
DEMANDS CREATED BY YEAR
Chart: 
| 2025 | 2026
Demands | 31 | 25
31
2025
25
2026
Notes: SOURCE: IMG_8CF6D7E4-E31F-4C6C-9E8E-7E059150168F.jpeg.
VERIFIED: Status counts are Completed 25, Baseline 1 15, Baseline 0 9 and Under Discussion 7. Demand origin totals are 31 for 2025 and 25 for 2026.
DERIVED: 45% completed is 25 divided by 56. The 24-demand baseline pipeline is 15 plus 9.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: This slide decomposes the portfolio position by lifecycle stage and year of demand creation.

## Slide 4
SUPPORTING PORTFOLIO
BUILD
20 supporting demands extend delivery across 11 platforms
Seven completed with 13 demands active in Baseline 0 or Baseline 1
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
04
20
SUPPORTING DEMANDS
11 platforms
Delivery spans core banking, mobile, FinOne and eight additional platforms.
LIFECYCLE POSITION
Completed
7
35%
Baseline 1
9
45%
Baseline 0
4
20%
13
ACTIVE BASELINE
65% of supporting demands are in Baseline 0 or Baseline 1
PLATFORM MIX
Chart: 
| Core Banking | Mobile Banking | FinOne | Other
Demands | 5 | 4 | 3 | 8
Other = eight platforms with one demand each
Notes: SOURCE: IMG_B8C720AD-BF08-4FAC-A6CA-DB10B99E906B.jpeg.
VERIFIED: 20 supporting demands: 7 Completed, 9 Baseline 1 and 4 Baseline 0 across 11 platforms. Platform counts are Core Banking Platform 5, Mobile Banking - Retail 4, FinOne 3 and eight other platforms with one demand each.
DERIVED: 35% completed is 7 divided by 20. Active baseline is 9 plus 4, equal to 13 or 65% of supporting demands. Platform counts were grouped directly from the 20 visible rows.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: The supporting portfolio extends Cards delivery across 11 platforms. Seven items are complete, while 13 remain active in Baseline 0 or Baseline 1. The largest concentrations sit in Core Banking, Mobile Banking and FinOne.

## Slide 5
CARDS SQUAD
BUILD
One Cards Squad supports delivery across the full portfolio
13 specialists connect leadership, delivery, engineering and assurance across 56 demands
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
05
PORTFOLIO LEADERSHIP
3
DELIVERY MANAGEMENT
3
ENGINEERING + ASSURANCE
7
EM
Ebrahim Hassan Marzoughi
AVP, Cards and ATM Technologies
TA
Tarek Mohamed AbdelAziz
Manager, Cards and ATM Tech.
HR
Habibur Rahman
Assistant Manager, Cards and ATM
Portfolio direction and accountable delivery ownership
LA
Leo Dilip Kumar Anthony
Projects Leader, Cards and ATM
SM
Syed Mujahid Hassan
Projects Leader, Cards and ATM
AS
Ashraf Shahidali Ansari
Technical Analyst
Demand shaping, project coordination and delivery tracking
AR
Abdul Rahman
Software Engineer
BE
Bilal Elkiri
Senior Software Engineer
HM
Heshmat Moffah
Senior Software Engineer
JJ
Jince Jose
PowerCard Developer
KB
Kamalakannan B.
System Test Engineer
MH
Muhammad Haris Azfar
Software Engineer
MU
Muhammad Umer Waqas
PowerCard Developer
Build, test and platform expertise across Cards delivery
ONE TEAM. FULL LIFECYCLE.
SHAPE
DELIVER
TEST
GO LIVE
Notes: SOURCE: IMG_8FDCA664-8D70-4187-80A2-1FCAAC74536A.jpeg, IMG_7D69CBF7-3197-4ACE-A4AA-A5CB9ECD8C38.jpeg and IMG_6C7E5331-A428-4C07-8298-460A4376BEA9.jpeg.
VERIFIED: 13 visible resources: Ebrahim Hassan Marzoughi; Abdul Rahman; Ashraf Shahidali Ansari; Bilal Elkiri; Habibur Rahman; Heshmat Moffah; Leo Dilip Kumar Anthony; Syed Mujahid Hassan; Tarek Mohamed AbdelAziz; Jince Jose; Kamalakannan B. (surname truncated in the source); Muhammad Haris Azfar; Muhammad Umer Waqas. Visible role labels are represented in concise form.
DERIVED: The three capability groups are derived from the visible reporting structure and role titles. The 56-demand portfolio is verified from the consolidated Cards demand statistics. The generic team illustration does not depict any named employee.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: The Cards Squad brings portfolio leadership, project delivery, engineering and assurance together across the full demand lifecycle.

## Slide 6
GO-LIVE ACHIEVEMENT
BUILD
25 go-lives completed, with seven scheduled through January 2027
Monthly go-live profile across 2025 to 2027
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
06
25
COMPLETED GO-LIVES
78% of 32 tracked
7
PLANNED GO-LIVES
Oct, Dec and Jan
The forward plan groups three releases in October, three in December and one in January 2027.
GO-LIVES BY MONTH
Completed
Planned
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Completed | 7 | 2 | 1 | 1 | 4 | 0 | 3 | 1 | 5 | 1 | 0 | 0
Planned | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3
OCT 2026
3 planned
DEC 2026
3 planned
JAN 2027
1 planned
Notes: SOURCE: IMG_9453F031-49AD-4FB5-A10C-0BBC67F65DBF.jpeg.
VERIFIED: 32 total go-lives: 25 completed and 7 planned. Completed monthly counts are Jan 7, Feb 2, Mar 1, Apr 1, May 4, Jun 0, Jul 3, Aug 1, Sep 5, Oct 1, Nov 0 and Dec 0. Planned counts are Oct 3, Dec 3 and Jan 2027 1.
DERIVED: 78% is 25 divided by 32, rounded to the nearest whole percentage.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: The slide shows delivered volume first, then locates the seven remaining scheduled go-lives by month.

## Slide 7
PROJECT OUTCOME
FLOURISH
Jaywan progressed from mono-badge launch to co-badging, tokenization and standards uplift
Verified delivery stages across the Jaywan programme
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
07
LIVE FOUNDATION
26 OCT
2025
Jaywan Mono-Badge Debit Cards
DMGT-993
Completed
PROGRAMME PROGRESSION
MAR 2026
E-commerce live
DMGT-1978 / 1979
CURRENT
Tokenization UAT
Integration in progress
11 DEC 2026
Visa co-badged card
Baseline 1
11 DEC 2026
Standards uplift V1.8
Baseline 1
ISSUANCE
Mono-badge live, with co-badged card in Baseline 1
DIGITAL PAYMENT
E-commerce live, with tokenization progressing
SCHEME READINESS
Standards uplift targets 11 December
Notes: SOURCE: IMG_B4D6B5BE-FBEC-4715-B676-719BF6C5D496.jpeg, IMG_FEC5FBBC-CA27-48A4-A3AF-826FD80105E2.jpeg and IMG_AB07E44D-4585-4840-86BD-501E4B809AE6.jpeg.
VERIFIED: DMGT-993 Jaywan Mono-Badge Debit Cards completed on 26 Oct 2025. DMGT-1978 and DMGT-1979 show e-commerce transactions live with tokenization access or UAT in progress. DMGT-1305 Jaywan Visa Co-Badged Debit Cards and DMGT-1863 Jaywan Standards Uplift to V1.8 are Baseline 1 with target date 11 Dec 2026.
DERIVED: The programme progression groups verified Jaywan demands by delivered and current stage; no benefit values are inferred.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Flourish.
NARRATIVE: The slide narrates the delivered Jaywan foundation and the verified expansion into co-badging, tokenization and scheme uplift.

## Slide 8
DELIVERY OUTCOMES
FLOURISH
Messaging and pricing changes span live delivery, UAT and scheduled go-lives
Two delivery tracks across customer communications and revenue propositions
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
08
CUSTOMER COMMUNICATIONS
23 FEB
International currency SMS
Completed
17 MAY
Failed transaction SMS
Completed
06 SEP
Declined SMS enhancement
Completed
UAT
Wrong expiry-date SMS
Baseline 1
18 OCT
Statement generation SMS
UAT target
REVENUE AND CARD PROPOSITIONS
26 APR
Digital Salam renewal
Completed
10 MAY
ENR pricing increase
Completed
06 SEP
Quasi-cash advance fee
Completed
23 OCT
ENR pricing change
Planned go-live
06 DEC
Emirati covered card
Planned go-live
15 JAN
Credit Shield
2027 plan
Notes: SOURCE: IMG_258ABD3F-5921-4186-BE6A-7CCD9666DF47.jpeg, IMG_B8FA6345-8936-40D1-9489-976E7D3715B3.jpeg, IMG_2210AAD2-88BA-438E-96E4-0142F1AE5012.jpeg, IMG_AB07E44D-4585-4840-86BD-501E4B809AE6.jpeg and IMG_FEC5FBBC-CA27-48A4-A3AF-826FD80105E2.jpeg.
VERIFIED: Customer communications: DMGT-242 completed 23 Feb 2026; DMGT-144 completed 17 May 2026; DMGT-2414 completed 6 Sep 2026; DMGT-2415 is in UAT; DMGT-1266 is in UAT with target 18 Oct 2026. Revenue and propositions: DMGT-125 completed 26 Apr 2026; DMGT-1960 completed 10 May 2026; DMGT-2143 completed 6 Sep 2026; DMGT-1329 targets 23 Oct 2026; DMGT-1680 targets 6 Dec 2026; DMGT-672 targets 15 Jan 2027.
DERIVED: The two tracks organize verified projects by business outcome theme. No financial benefit values are inferred.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Flourish.
NARRATIVE: The slide shows how delivered customer communications connect to UAT work and scheduled proposition releases.

## Slide 9
CONTROL OUTCOME
PROTECT
Six audit and regulatory deliveries entered production across Cards platforms
Completed control-related delivery from October 2025 to September 2026
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
09
6
CONTROL DELIVERIES
2 audit items
4 regulatory items
Production dates span 26 October 2025 to 3 September 2026.
CONTROL DELIVERY TIMELINE
26 OCT 25
Jaywan mono-badge
Regulatory
25 JAN
New fee code
Audit
15 MAR
DPD statement fix
Regulatory
17 MAY
PIN counter reset
Audit
17 MAY
LPC fees
Regulatory
03 SEP
Visa clearing exchange
Regulatory
CURRENT CONTROL PIPELINE
POS and ATM report changes
Fraud-prevention data elements
Loyalty database server upgrade
Notes: SOURCE: IMG_B4D6B5BE-FBEC-4715-B676-719BF6C5D496.jpeg, IMG_258ABD3F-5921-4186-BE6A-7CCD9666DF47.jpeg, IMG_B8FA6345-8936-40D1-9489-976E7D3715B3.jpeg and IMG_69F75D47-98CE-4A3A-B11C-84351EC9E8F3.jpeg.
VERIFIED: Six completed audit or regulatory deliveries shown: DMGT-993 on 26 Oct 2025; DMGT-1307 on 25 Jan 2026; DMGT-982 on 15 Mar 2026; DMGT-1091 and DMGT-984 on 17 May 2026; DMGT-1780 on 3 Sep 2026. Current control pipeline examples are DMGT-2345, DMGT-1570 and DMGT-651.
DERIVED: Two audit items and four regulatory items are counted from the verified demand segment classifications shown in the screenshots.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Protect.
NARRATIVE: The slide consolidates completed control outcomes and three verified items still in planning or delivery.

## Slide 10
DELIVERY ROADMAP
BUILD
Seven planned go-lives concentrate in October, December and January
Named forward releases through 15 January 2027
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
10
3
OCTOBER 2026
3
DECEMBER 2026
1
JANUARY 2027
10 OCT
DMGT-2162
Central Bank STFP file automation
18 OCT
DMGT-1266
Covered Card statement SMS
23 OCT
DMGT-1329
ENR pricing change
06 DEC
DMGT-1680
New Emirati Covered Card
11 DEC
DMGT-1305
Jaywan Visa co-badged debit card
11 DEC
DMGT-1863
Jaywan standards uplift V1.8
15 JAN
DMGT-672
Credit Shield enrolment
Notes: SOURCE: IMG_9453F031-49AD-4FB5-A10C-0BBC67F65DBF.jpeg plus IMG_FEC5FBBC-CA27-48A4-A3AF-826FD80105E2.jpeg, IMG_AB07E44D-4585-4840-86BD-501E4B809AE6.jpeg, IMG_69F75D47-98CE-4A3A-B11C-84351EC9E8F3.jpeg and IMG_2210AAD2-88BA-438E-96E4-0142F1AE5012.jpeg.
VERIFIED: The seven planned go-lives reconcile to the pivot: 3 in Oct 2026, 3 in Dec 2026 and 1 in Jan 2027. The named projects and target dates are DMGT-2162 10 Oct; DMGT-1266 18 Oct; DMGT-1329 23 Oct; DMGT-1680 6 Dec; DMGT-1305 and DMGT-1863 11 Dec; DMGT-672 15 Jan 2027.
DERIVED: The roadmap aligns the seven named project dates to the monthly planned counts in the consolidated go-live pivot.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Build.
NARRATIVE: The slide converts the monthly plan into a named executive delivery roadmap.

## Slide 11
EXECUTIVE SYNTHESIS
FLOURISH
Delivery stands at 25 completed, 24 active baseline and seven under discussion
Current portfolio position and confirmed forward go-live plan
Source: user-provided Cards portfolio screenshots. Data basis is identified in speaker notes.
11
56
TOTAL DEMANDS
2025 and 2026 origin
25
COMPLETED
45% of portfolio
24
ACTIVE BASELINE
15 B1 + 9 B0
7
UNDER DISCUSSION
Technology review
DELIVERED
25
completed go-lives
CURRENT DELIVERY
24
demands in Baseline 0 or 1
FORWARD PLAN
7
planned go-lives
LAST CONFIRMED DATE
15 JAN 2027
Credit Shield enrolment
The portfolio closes with 25 completed demands and a seven-item go-live plan through 15 January 2027.
Notes: SOURCE: IMG_8CF6D7E4-E31F-4C6C-9E8E-7E059150168F.jpeg, IMG_9453F031-49AD-4FB5-A10C-0BBC67F65DBF.jpeg and project screenshots supporting the seven planned releases.
VERIFIED: 56 total demands; 25 completed; 15 Baseline 1; 9 Baseline 0; 7 under discussion; 25 completed go-lives; 7 planned go-lives; final named target is DMGT-672 Credit Shield enrolment on 15 Jan 2027.
DERIVED: 24 active baseline demands is 15 plus 9. 45% completed is 25 divided by 56, rounded to the nearest whole percentage.
SIMULATED: None displayed.
IT STRATEGY PILLAR: Flourish.
NARRATIVE: The closing slide restates the delivery position and the confirmed horizon of the forward plan without adding recommendations.